## Resource Plan - Approved
Resource Plan
|  |  |  | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23
|  |  |  | DEV | DEV | UAT | UAT | TTT | REL | SS | SS | SS | SS | PFS11 | PFS12 | PFS13 | PFS14 | PFS15 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | Total Hours | Total Expense
Resource | Type | Role | Rate | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned
Oscar Sadder | OnShore | PD | 165 | 2019-07-29: 2; 2019-08-05: 2; 2019-08-12: 2; 2019-08-19: 2; 2019-08-26: 2; 2019-09-02: 2; 2019-09-09: 2; 2019-09-16: 2; 2019-09-23: 2; 2019-09-30: 2 | 20 | 3300
Agustin Galindo | OnShore | PM | 165 | 2019-07-29: 10; 2019-08-05: 10; 2019-08-12: 10; 2019-08-19: 10; 2019-08-26: 10; 2019-09-02: 10; 2019-09-09: 10; 2019-09-16: 10; 2019-09-23: 10; 2019-09-30: 10 | 100 | 16500
Scott Soulgares | OnShore | BA | 165 | 2019-07-29: 8; 2019-08-05: 20; 2019-08-12: 10; 2019-08-19: 10; 2019-08-26: 10; 2019-09-02: 10; 2019-09-09: 10; 2019-09-16: 10; 2019-09-23: 10; 2019-09-30: 10 | 108 | 17820
Vladimir Belomenstnov | OnShore | DEV | 165 | 2019-07-29: 10; 2019-08-05: 20; 2019-08-12: 10; 2019-08-19: 10; 2019-08-26: 10; 2019-09-02: 10; 2019-09-09: 10; 2019-09-16: 10; 2019-09-23: 10; 2019-09-30: 10 | 110 | 18150
Mounica Chadaram | OnShore | DEV | 165 | 2019-07-29: 10 | 10 | 1650
Kris Wiklund | OnShore | DEV | 165 | 2019-07-29: 8; 2019-08-05: 16; 2019-08-12: 16; 2019-08-19: 16; 2019-08-26: 32; 2019-09-02: 8; 2019-09-09: 8 | 104 | 17160
Naveem Jeevanandam | OnShore | DEV | 165 | 2019-08-05: 20; 2019-08-12: 20; 2019-08-19: 10; 2019-08-26: 10 | 60
Manuel Gahona | OnShore | DEV | 165 | 2019-07-29: 10; 2019-08-05: 10; 2019-08-12: 10; 2019-08-19: 10; 2019-08-26: 10; 2019-09-02: 10; 2019-09-09: 10; 2019-09-16: 10; 2019-09-23: 10; 2019-09-30: 10 | 100 | 16500
|  |  | Total OnShore Hours per Week | 58 | 98 | 78 | 68 | 84 | 50 | 50 | 42 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 100980
|  |  | Total OnShore Hours per Week | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total Resource Hours | 58 | 98 | 78 | 68 | 84 | 50 | 50 | 42 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total OnShore Expense | 9570 | 16170 | 12870 | 11220 | 13860 | 8250 | 8250 | 6930 | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100980
|  |  | Total OffShore Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total Expense | 9570 | 16170 | 12870 | 11220 | 13860 | 8250 | 8250 | 6930 | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100980
|  |  |  | 2019-11-04: Available Budget as of 07/28 | 462.25
[26 empty] | 149.75 | Aprox | bar: 2019-11-04
Fill in Weeks
Fill in Week Numbers
Fill in Rates
Fill in Types
Fill in Names
Use Copy/Insert Copied Columns to extend weeks
Use Copy/Insert Copied Rows to Add more resources
Add forecasted hours

## EVM
PERIOD
ID | DELIVERABLE TITLE | Task Rate | Total Budget | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23
|  |  |  | DEV | DEV | UAT | UAT | TTT | REL | SS | SS | SS | SS | PFS11 | PFS12 | PFS13 | PFS14 | PFS15 | WK22 | WK23 | PFS12 | PFS13 | PFS14 | PFS15 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28
1 | Project Management / Oversight | 165 | 19800 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [18 empty] | 120 | x
2 | Functional Workstream - CRM Configuration | 165 | 16800 | 18 | 40 | 30 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | [18 empty] | 178 | x
3 | Portal Configuration | 165 | 45200 | 20 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [18 empty] | 210
4 | Training | 165 | 17160 | 8 | 16 | 16 | 16 | 32 | 8 | 8 | [21 empty] | 104 | x
| TOTAL BUDGETED HOURS |  | 612 | 58 | 98 | 78 | 68 | 84 | 50 | 50 | 42 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612
BAC | TOTAL BUDGETED COST |  | 100980 | 9570 | 16170 | 12870 | 11220 | 13860 | 8250 | 8250 | 6930 | 6930 | 6930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PV | CUMLATIVE PLANNED VALUE |  |  | 9570 | 25740 | 38610 | 49830 | 63690 | 71940 | 80190 | 87120 | 94050 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980 | 100980
ACTUAL COST
|  | WORK ENDING |  | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29
|  | (ONSHORE) ACTUAL HOURS | 177.5 | 102 | 75.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (ONSHORE) ACTUAL COST | 29287.5 | 16830 | 12457.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (OFFSHORE) ACTUAL HOURS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | (OFFSHORE) ACTUAL COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC |  | CUMULATIVE ACTUAL COST |  | 16830 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5 | 29287.5
EARNED VALUE
EV |  | CUMULATIVE EARNED VALUE |  | 6520 | 8264 | 8220 | 1680 | 268800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT PERFORMANCE METRICS
CV |  | COST VARIANCE | ( EV – AC ) | -10310 | -21023.5 | -21067.5 | -27607.5 | 239512.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5 | -29287.5
SV |  | SCHEDULE VARIANCE | ( EV – PV ) | -3050 | -17476 | -30390 | -48150 | 205110 | -71940 | -80190 | -87120 | -94050 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980 | -100980
CPI |  | COST PERFORMANCE INDEX | ( EV / AC ) | 0.3874 | 0.28217 | 0.28067 | 0.057362 | 9.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPI |  | SCHEDULE PERFORMANCE INDEX | ( EV / PV ) | 0.6813 | 0.32106 | 0.2129 | 0.033715 | 4.2204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EAC |  | ESTIMATED COST AT COMPLETION |  | 260658.4969 | 357871.7026 | 359787.3175 | 1760387.946 | 11002.4247 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
A cost performance index higher than 1.0 indicates that the project is costing less than expected; one that’s less than 1.0 indicates a project that’s costing more than expected.
A schedule performance index higher than 1.0 indicates that the project is ahead of schedule; one that’s below 1.0 indicates that it’s running behind schedule.
434.5
Setup:
Fill in Deliverable Titles
Fill in Rates
Use Copy/Insert Copied Columns to extend weeks
Use Copy/Insert Copied Rows to Deliverable Titles
Plot Forecasted hours against Deliverables
Confirm Total Budgeted hours = Total Resource Weekly Totals
Weekly:
** Relies on Weekly Actuals to be updated first
Copy EVM calculations from previous week to current week
Update Chart Data

## EV WORKSHEET
PERIOD
ID | DELIVERABLE TITLE | Total Budget | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-12-02 | 2019-12-09 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23
|  |  | DEV | DEV | UAT | UAT | TTT | REL | SS | SS | SS | SS | PFS11 | PFS12 | PFS13 | PFS14 | PFS15 | PFS13 | PFS14 | PFS15 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28
1 | Project Management / Oversight | 12800 | 10% | 18%
2 | Functional Workstream - CRM Configuration | 16800 | 0% | 0% | 0% | 10% | 16
3 | Portal Configuration | 45200 | 10% | 10% | 15%
4 | Training | 14400 | 5% | 10% | 10%
EV | CUMULATIVE EARNED VALUE | 89200 | 6520 | 8264 | 8220 | 1680 | 268800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Setup: | [7 empty] | 9 | 50%
| Confirm Titles, Weeks, Budget colums/rows copied correctly | [7 empty] | 1 | 5.556%
Use Copy/Insert Copied Columns to extend weeks
Use Copy/Insert Copied Rows to Deliverable Titles
Weekly:
| Update % Complete for the week per Deliverable | [5 empty] | Functional | Wkst1 | 0.7937%
| ** Relies on Project Plan to be updated | [5 empty] | 7 | Wkst2 | 1.02%
[8 empty] | Wkst3 | 1.02%
[8 empty] | Wkst4 | 1.02% | [18 empty] | 100
[8 empty] | Wkst5 | 1.02%
[8 empty] | Wkst6 | 1.02%
[8 empty] | Wkst7 | 1.02%

## ACTUALS
Type | Employee | Task | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Total | Week Ending | Type | Rate
Billable | Agustin Galindo | [8 empty] | 5 | 2019-08-04 | OnShore | 165
Billable | Mounica Chadaram | [8 empty] | 40 | 2019-08-04 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 26 | 2019-08-04 | OnShore | 165
Billable | Vladimir Belomestnov | [8 empty] | 31 | 2019-08-04 | OnShore | 165
Billable | Agustin Galindo | [8 empty] | 7 | 2019-08-11 | OnShore | 165
Billable | Kris Wilklund | [8 empty] | 16 | 2019-08-11 | OnShore | 165
Billable | Naveen Kumar Jeevanandam | [8 empty] | 12 | 2019-08-11 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 11 | 2019-08-11 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 10 | 2019-08-11 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 1.5 | 2019-08-11 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 3.5 | 2019-08-11 | OnShore | 165
Billable | Scott Soulages | [8 empty] | 0.5 | 2019-08-11 | OnShore | 165
Billable | Vladimir Belomestnov | [8 empty] | 14 | 2019-08-11 | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable
Billable
Billable
Billable
Billable
Billable
Billable
Billable
Billable
Billable
Billable
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [9 empty] | 0 |  | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
Billable | [11 empty] | OnShore | 165
177.5